## Sheet1
Site Name | Postcode | Sub Area | Sport | Security of Use | Surface | Management | Status | Total Capacity Position | Aim | Action | Priority | Partners | Timescales | Cost
Adams Recreation Ground | CA27 0EW | North | Football | Secured | Grass | Community Organisation | Four poor quality non-floodlit pitches one each 11v11 adult, youth 11v11, youth 9v9 and youth 7v7 with standard quality ancillary facilities on-site | No spare capacity | Protect, Enhance | Improve pitch quality to support additional community use, based the maintenance regime recommended in the completed Pitch Power report. Remove all training demand from site, and relocate on 3G provision | H | Sports Club, Trust, CBC | S | M
Ashlea Rd, Egremont | CA22 2JA | North |  | Unused | Grass | Local Authority | Unused | Unused | Unused | Unused | L | CBC
Beckermet C of E School | CA21 2YB | North | Football | Unsecured | Grass | Education | The education site has one standard quality non-floodlit youth 11v11 pitch with access to the school changing rooms as ancillary facilities | 1 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education, FF, FA | M | L
Beckermet CofE Primary School | CA21 2YB | North | Netball | Unsecured | Tarmac | Education | This is a primary school site, with netball markings but mainly used as a playground for the school. The markings are slightly faded. The court is adjacent to a small sided football pitch, also owned by the primary school. | No capacity due to lack of floodlighting | Protect | Sustain court quality for curricular use | L | Education | M | L
Bishops Park |  | North | Football | Unsecured | Grass | Sports Club | One poor-quality adult 11v11 pitch with no availability of any ancillary facilities | No spare capacity | Protect, Enhance | Improve pitch quality to support additional community use | H | Education | S | M
Black Combe Junior School | LA18 5DT | South | Football | Unsecured | Grass | Education | Two standard quality youth 7v7 pitches with access to the school changing rooms as ancillary facilities | 2 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education, FF, FA | M | L
Bootle AFC | LA19 5UL | Central | Football | Secured | Grass | Sports Club | One average-quality adult 11v11 pitch with standard quality ancillary facilities but no provision for floodlights on-site | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use, based on recommendations in the completed PP report | M | Sports Club, Community organisation | M | L
Cleator Moor Activity Centre | CA25 5AN | North | AGP | Secured | 3G | Private | One good quality full-sized floodlit 3G pitch which is world rugby compliant with good ancillary facilities. The pitch was refurbished in 2021 | No spare capacity | Protect | Sustain pitch quality and ensure community use is maximised | H | CBC, FA, FF and GLL | L | L
Cleator Moor Bowls Club | CA25 5DB | North | Outdoor Bowls | Secured | Grass | Sports Club | 6 rink court. good quality surface but slightly patchy in places. Small but good facilities and clubhouse. Poor sign posting | Spare capacity | Protect | Ensure site quality does not worsen | L | Sports Club | L | L
Cleator Moor Celtic FC | CA25 5JB | North | Football | Secured | Grass | Sports Club | One good quality adult 11v11 pitch and standard ancillary facilities. The club has recently completed an extensive drainage project with Football Foundation Support | No spare capacity | Protect | Sustain pitch quality for club use in line with Pitch Power recommendations | H | Sports Club, Diocese | M | L
Cleator Recreation Ground |  | North | Football | Secured | Grass | Local Authority | The local authority owned and managed site has three pitches of standard quality. These pitches include adult 11v11, youth 9v9 and youth 7v7. However, there is no provision for ancillary facilities | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use, based on PP report from Jan 2023. Relocate all training demand from grass pitches onto 3G provision | H | CBC, FA, FF, Sports club | S | M
Coniston Avenue Playing Field | CA20 1QX | Central | Football | Secured | Grass | Local Authority | The site has one adult 11v11 pitch of poor quality and there is an absence of any ancillary facility | 1 MES spare | Protect, Enhance | Improve pitch quality to support additional community use | H | CBC, FA, FF | S | L
Cumbria Sport Academy | CA28 8SD | North | Football | Secured | Grass | Trust | Cumbria Sport Academy has two non-floodlit adult 11v11 pitches of good quality and adequate ancillary facilities | 2 MES spare | Protect | Sustain pitch quality for club use | L | Trust, FA | M | L
Cumbria Sport Academy | CA28 8SD | North | AGP | Secured | 3G | Trust | One poor rated 80x30 floodlit 3G pitch neither FA registered nor world rugby compliant but offers good quality ancillary facilities | Spare capacity | Protect | Sustain pitch quality and ensure community use is maximised | L | Trust, FA | L | L
Distington ARLFC | CA14 5XU | North | Rugby League | Secured | Grass | Sports Club | One good quality floodlit senior pitch with even grass and Sport England funded changing rooms is a shared facility between Distington ARLFC and Grass Road Sharks FC. However, it has a football pitch which was incorrectly marked at the time of the visit. | No spare capacity | Protect | Sustain pitch quality through current maintenance regime | L | Sports Club, RFL, CBC | L | L
Distington ARLFC | CA14 5XG | North | Football | Secured | Grass | Sports Club | There is one standard quality youth 11v11 pitch as well as good ancillary facilities | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use | M | RFL, Sports Club | M | L
Egremont Bowling Club | CA22 2QB | North | Outdoor Bowls | Secured | Grass | Sports Club | 1x 6 rink court. Average surface - good grass coverage, but slightly patchy at time of visit. Good to average clubhouse. Adequate parking and good access | Spare capacity | Protect | Ensure site quality does not worsen | L | Sports Club | L | L
Egremont RUFC | CA22 2NL | North | Rugby Union | Secured | Grass | Sports Club | One good quality senior pitch partly floodlit with good quality maintenance and ancillary facilities | -0.75 | Protect, Provide | Explore the development of WR22 3G pitch in partnership with FF to provide additional capacity for local football clubs. Ongoing work needed at Stage E to fully inform the impact of development. Sustain current maintenance routine and grass pitch quality | L | RFU, Sports Club, FF | L | H
Egremont RUFC | CA22 2NL | North | AGP | Secured | 3G | Sports Club | One standard quality 5v5 floodlit 3G pitch neither FA registered nor world rugby compliant but with good ancillary facilities. The pitch was refurbished in 2008 | Spare capacity | Protect, Provide | Protect existing small sided provision, develop additional 3G pitch facility, as highlighted in the rugby union section. | M | Club, RFU, FF | S | H
Eskdale | CA19 1TD | Central | Cricket | Secured | Grass | Sports Club | One, four wicket grass square with no ancillary facilities. The site is used for friendly fixtures only. | 6 MPS spare | Protect | Sustain pitch quality for club use | M | Club, ECB, CCB | M | L
Fairfield (Arlecdon ARLFC) | CA26 3XD | North | Rugby League | Secured | Grass | Sports Club | One non-floodlit standard quality uneven unmarked pitch recorded as junior but evidence of master's use with standard ancillary facilities | No spare capacity | Protect, Enhance | Improve pitch quality for community use e.g. drainage | M | Sports Club, RFL, CBC | M | M
Former Ehenside School fields |  | North | Rugby League | Unused | Grass | Education | Unused | Unused | Unused | Unused | L | CBC | L | L
Frizington Bowls Club | CA26 3PX | North | Outdoor Bowls | Secured | Grass | Sports Club | 5 rink court. Satisfactory surface. Very small clubhouse with kitchen and communal facilities | Spare capacity | Protect | Ensure site quality does not worsen | M | Sports Club | L | L
Frizington Jubilee Field | CA26 3PF | North | Rugby League | Unsecured | Grass | Sports Club | One unused non-floodlit local authority owned senior pitch of poor quality which is uncut and with a lack of ancillary facilities. The pitch unlikely to be used to meet any current or future rugby league demand. | 1 MES spare | Protect, Enhance | Improve pitch quality for community use e.g. drainage. This should be the responsibility of the FA and FF, as all current demand is generated by football clubs. | H | Sports Club, FA, FF, CBC | S | M
Gillfoot Park | CA22 2QU | North | Cricket | Secured | Grass | Sports Club | The site is shared with rugby league which has one high-quality pitch with 18 squares, no non-turf wickets, a small boundary, an excellent clubhouse with excellent nets. Several containers suggest suitable maintenance equipment | 50 MPS spare | Protect | Sustain pitch quality for club use | M | Club, ECB, CCB | M | L
Gillfoot Park (Egremont Rangers) | CA22 2QU | North | Rugby League | Secured | Grass | Sports Club | One excellent quality senior floodlit pitch and high-quality changing rooms on-site with the club looking to develop another site at 'Tarpot Pitch' | No spare capacity | Protect | Sustain pitch quality through current maintenance regime | L | Sports Club | L | L
Gosforth C of E School | CA20 1AZ | Central | Football | Unsecured | Grass | Education | One poorly maintained 7v7 pitch with access to the school changing rooms as ancillary facilities | 1 MES spare | Protect, Enhance | Improve pitch quality to support additional community use | H | Education, FF, FA | S | L
Gosforth CofE Community Primary School | CA20 1AZ | Central | Netball | Unsecured | Tarmac | Education | This is a primary school site, with netball markings overlayed with small sided football. The site is mainly used as a playground for the school. The markings are slightly faded. | No capacity due to lack of floodlighting | Protect | Sustain court quality for curricular use | L | Education | M | L
Gosforth Playing Field | CA20 1AY | Central | Football | Secured | Grass | Local Authority | One standard quality adult 11v11 pitch used by Go's Fourth Juniors FC and Gosforth AFC has a provision of standard ancillary facilities | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use | M | CBC, FA, FF | M | L
Greenbank Sports Field |  | North | Football | Unused | Grass | Local Authority | Unused | Unused | Unused | Unused | L | CBC | L | L
Harras Moor | CA28 6SJ | North | Football | Unused | Grass | Local Authority | Unused | Unused | Unused | Unused | L | CBC | L | L
Haverigg | LA18 4ES | South | Tennis | Secured | Tarmac | Local Authority | Poor quality tarmac court, with no fencing. An old adjacent court has been converted into a MUGA. The court needs resurfacing to be suitable to sustain tennis play. The court is highlighted by the LTA as a priority for improvement. | Spare capacity | Enhance | Improve court quality for community use | H | CBC, LTA | S | H
Haverigg Cricket Club | LA18 4EW | South | Cricket | Secured | Grass | Sports Club | The ground located adjacent to the sea is of good quality, with one pitch, 4 squares and quality ancillary facilities. In particular the bar is a well-used community facility | 30 MPS spare | Protect | Sustain pitch quality for club use | M | Club, ECB, CCB | M | L
Hensingham ARLFC | CA28 8TX | North | Rugby League | Secured | Grass | Sports Club | One non-floodlit good pitch with standard facilities and easy access but limited parking | No spare capacity | Protect, Enhance | Improve pitch quality for community use e.g. drainage | H | Sports Club, RFL | S | M
Hensingham Primary School | CA28 8QZ | North | Football | Not available | Grass | Education | One standard-quality 11v11 pitch with access to the school changing rooms as ancillary facilities are not available for community use | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education | M | L
Homewood Hill |  | North | Football | Unused | Grass | Local Authority | Unused | Unused | Unused | Unused | L | CBC | L | L
JD Campbell Memorial Ground | CA23 3DD | North | Cricket | Secured | Grass | Sports Club | One high-grade pitch with 10 squares but poor ancillary facilities | 12 MPS spare | Protect | Sustain pitch quality for club use | M | Club, ECB, CCB | M | L
Kells ARLFC - Haig Pit | CA28 9EJ | North | Rugby League | Secured | Grass | Sports Club | There is one local authority owned, standard quality pitch with a slight slope, of which half is floodlit with perimeter fencing and adequate car parking. Kells ARLFC has 2 sites and a clubhouse which is in a different location which includes a bar changing rooms and gym. | No spare capacity | Protect | Sustain pitch quality through current maintenance regime | M | Sports Club, CBC | M | L
Kells ARLFC - Welfare Ground, High Road | CA28 9EJ | North | Rugby League | Secured | Grass | Sports Club | The other Kells ARLFC site which is owned by the sports club has a non-floodlit standard quality pitch with a clubhouse which is in a different location which includes a bar changing rooms and gym | No spare capacity | Protect, Enhance, Provide | Explore the potential and need for 3G development that is rugby league compliant as part of Stage E. Improve pitch quality for community use e.g. drainage | H | Sports Club, RFL | L | H
Kells Welfare, High Road | CA28 9PQ | North | Football | Secured | Grass | Local Authority | One standard quality adult 11v11 pitch with a lack of any ancillary facilities | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use | M | CBC, FA, FF | M | L
Lowca ARLFC | CA28 6PH | North | Rugby League | Secured | Grass | Sports Club | One excellent quality senior pitch with 3 floodlights for training, a quality clubhouse, ample parking and easy accessibility for both rugby and football | No spare capacity | Protect | Sustain pitch quality through current maintenance regime | L | Sports Club, RFL, CBC | L | L
Lowca ARLFC | CA28 6PH | North | Football | Secured | Grass | Sports Club | One standard quality adult 11v11 pitch available with good quality ancillary facilities | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use | M | RFL, Sports Club | M | L
Millom Cricket Club | LA18 5DW | South | Cricket | Secured | Grass | Sports Club | Milliom Cricket club's home ground is located in a residential area. It comprises of one high quality pitch, eight grass squares and good quality ancillary facilities including a separate box for scorers. There is limited parking available on-site and accessibility is an issue. The site is used by young people during school holidays indicating informal community use of nets | 4 MPS spare | Protect | Sustain pitch quality for club use | M | Club, ECB, CCB | M | L
Millom Park | LA18 4LA | South | Outdoor Bowls | Secured | Grass | Local Authority | Good quality surface and basic ancillary facilities | Spare capacity | Protect | Ensure site quality does not worsen | M | CBC, Sports Club | L | L
Millom Park | LA18 4LA | South | Tennis | Secured | Macadam | Local Authority | Two good quality macadam courts on a park site, located next to a MUGA, outdoor bowling rink and children’s play area. There is a small hut, which is meant for basic ancillary facilities (toilets and small kitchen), however this is mostly unused. The site is listed as an official LTA Cumbria venue | Spare capacity | Protect | Sustain court quality for community use | H | CBC, LTA | M | L
Millom RLFC | LA18 4PG | South | Rugby League | Secured | Grass | Sports Club | Two excellent pitches of which the training pitch is floodlit with a number of top ancillary facilities like clubhouse, bar and gym | No spare capacity | Protect | Sustain pitch quality through current maintenance regime | L | Sports Club | M | L
Millom RLFC - Hanna Field | LA18 4PG | South | Football | Secured | Grass | Sports Club | One ordinary non-floodlit adult 11v11 pitch with good quality ancillary facilities | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use, based on completed PP recommendations | M | RFL | M | L
Millom RUFC | LA18 4GY | South | Rugby Union | Secured | Grass | Sports Club | Two average quality senior pitches, one of which is floodlit with standard ancillary facilities and a poor maintenance programme | -2 | Protect, Enhance | Improve maintenance regime through engagement with the GMA to increase pitch capacity and lower current overplay. | L | Sports Club, RFU | S | M
Millom RUFC | LA18 4GY | South | Football | Secured | Grass | Sports Club | One adult 11v11 pitch and two youth 11v11 pitches of standard quality are on site with ancillary facility | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use | M | RFU, Sports Club | M | L
Millom School | LA18 5AB | South | Rugby League | Unsecured | Grass | Education | Two standard quality pitches, the larger pitch shared with rugby union, and the smaller one used for 9v9 games and access to school changing facilities | 2 MES spare | Protect, provide | Explore the potential and need for 3G development that is rugby league compliant as part of Stage E. Improve pitch quality for community use e.g. drainage and maximise community use | H | Education, RFL, FF, FA | S | H
Millom School | LA18 5AB | South | Cricket | Unsecured | Grass | School/College/University | The school has a large grass field with two, single grass wicket squares. | 5 MPS spare | Protect | Sustain pitch quality for curricular use seek community use agreement | H | Education, ECB CCB | M | L
Millom School | LA18 5AB | South | Football | Unsecured | Grass | Education | One poor quality adult 11v11 pitch and one poor youth quality 9v9 pitch with access to the school changing rooms as ancillary facilities | 1 MES spare | Protect, Enhance | Explore the potential for 3g development on the exisiting sand dressed AGP through ongoing work at stage E. Improve grass pitch quality to support additional community use | H | Education, FF, FA | H | L
Millom School | LA18 5AB | South | AGP | Unsecured | Sand Dressed | Education | One poor quality full-sized floodlit sand-dressed pitch neither FA registered nor world rugby compliant with access to the school changing rooms. The pitch was refurbished in 2006. There is no hockey usage of the pitch, by either the school or any club. | Spare capacity | Protect, Enhance, Provide | Explore the impact of resurface exisiting sand-dressed to full size 3G AGP. Stage E to explore the demand for rugby league usage of potential 3G development and whether it should be rugby compliant | H | Education, FF, FA, RFL | S | H
Millom School | LA18 5AB | South | Netball | Unsecured | Tarmac | Education | Millom School has two tarmac, standard quality courts, overlaid on three tennis courts. The site is a typical school tennis and netball facility and is likely also used as a multi-use area during break and lunchtimes for the school. The line markings are slightly worn. Although the courts are available for community use, there is no current agreement in place | No capacity due to lack of floodlighting | Protect | Sustain court quality for curricular use | L | Education | M | L
Millom School | LA18 5AB | South | Tennis | Unsecured | Tarmac | Education | Millom School has three tarmac, standard quality tennis courts, overlayed on two netball courts. The site is a typical school tennis and netball facility and is likely also used as a multi-use area during break and lunchtimes for the school. The line markings are slightly worn. | Spare capacity | Protect | Sustain court quality for curricular and community use | M | Education | M | L
Millom St James | LA18 4AS | South | Football | Secured | Grass | Sports Club | Millom Junior Football Club comprises of one standard quality non-floodlit adult 11v11 pitch with no ancillary facilities | No spare capacity | Protect | Review maintenance regime and sustain pitch quality for community use, based on completed PP recommendations | M | CBC, FA, FF, Sports club | M | L
Moor Row Community Primary School | CA24 3JW | North | Football | Unsecured | Grass | Education | One poor quality youth 11v11 pitch and one poor youth quality 9v9 pitch with access to the school changing rooms as ancillary facilities | No spare capacity | Protect, Enhance | Improve pitch quality to support additional community use | H | Education, FF, FA | M | L
Moresby RUFC | CA28 8XW | North | Rugby Union | Secured | Grass | Sports Club | One non-floodlit poor quality pitch with below average maintenance scores and poor ancillary facilities | 0 | Protect, Enhance | Installation of formal drainage solution and improved maintenance regime starting with pitch assessment through the GMA. Investment in ancillary facilities to raise standard provide additional changing facilities | H | Sports Club, RFU | L | H
Moresby RUFC | CA28 8XW | North | Football | Secured | Grass | Sports Club | One poor quality youth 9v9 pitch and ancillary facilities is used by two clubs | No spare capacity | Protect, Enhance | Improve pitch quality to support additional community use, based on completed PP recommendations. The site is significantly overplayed, due to poor quality surface. Remove all training demand from grass pitches and relocate on 3G provision. | H | RFU, Sports Club | S | M
SASRA Sports Complex / Windscale Squash & Fitness Club | CA22 2QN | North | Football | Secured | Grass | CSSC | Four standard quality non-floodlit pitches which include two adult 11v11, youth 11v11, one youth 9v9 and a youth 7v7 with standard quality ancillary facilities on-site | 3 MES spare | Protect, Enhance | Improve pitch quality to support additional community use, based on PP recommendations | H | Trust, FA | S | M
Seascale Primary School | CA20 1LZ | Central | Football | Unsecured | Grass | Education | One standard quality youth 11v11 pitch with standard ancillary facilities in the form of school changing rooms | 1 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education, FF, FA | M | L
Seascale Sports Hall | CA20 1QD | Central | Cricket | Secured | Grass | Local Authority | The site owned and run by the local authority has one pitch with 8 squares with roll out netting provided and no provision for artificial nets. The outfield grass is very long in some parts and flowering in some making it a poor facility overall | 2 MPS spare | Protect, Enhance | Sustain pitch quality for club use and unsure regular maintenance schedule is followed | H | ECB, CCB, CBC | S | L
Seascale Sports Hall | CA20 1QD | Central | Outdoor Bowls | Secured | Grass | Local Authority | 1x 7 rink court. Good quality. Good grass coverage. Busy at time of visit. Good parking and easy access. Good quality clubhouse facility - typical bowls club standard | Spare capacity | Protect | Ensure site quality does not worsen | M | CBC, Sports Club | L | L
Seascale Tennis Club | CA20 1PJ | Central | Tennis | Secured | Macadam | Sports Club | 3x asphalt courts. Good condition surface. Good condition netting. No floodlights. Average exterior fencing. Easy access, good parking. No evidence of improper use. Good clubhouse facilities | Spare capacity | Protect | Sustain court quality for community use | M | Sports Club | M | L
Silecroft | LA18 4NS | South | Tennis | Secured | Tarmac | Local Authority | One poor quality tarmac tennis court, with poor fencing and currently no netting. The site is not easily accessed and would require some resurfacing work to ensure its suitability for competitive tennis. Although there are no other line markings, there are signs of other use of the site, such as casual football | Spare capacity | Enhance | Improve court quality for community use | L | CBC | M | H
St Bees School | CA27 0DS | North | Rugby Union | Unsecured | Grass | Education | Two high quality floodlit well maintained senior pitches with access to school changing facilities | 0 | Protect, Enhance | Improve pitch quality and develop community use agreement | M | Education, RFU | S | L
St Bees School | CA27 0DS | North | Cricket | Unsecured | Grass | School/College/University | An independent school site with one pitch and no squares present at time of visit, but a well-maintained outfield. Two artificial nets with good surface condition, but poor netting and scoreboard present on-site. The pavilion and rolling equipment are in good condition. | No spare capacity | Protect, Enhance | Ensure grass wickets are present during the season and seek community use agreement | H | Education, ECB CCB | S | L
St Bees School | CA27 0DS | North | Football | Unsecured | Grass | Education | The education site has one standard quality non-floodlit youth 11v11 pitch with access to the school changing rooms as ancillary facilities | 1 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education, FF, FA | M | L
St Bees School | CA27 0DS | North | Tennis | Unsecured | Macadam | Education | Independent school. 3x asphalt courts. No nets present when visited. Average surface. No floodlights. Fencing poor | Spare capacity | Protect | Sustain court quality for curricular and community use | M | Education | M | L
St Bees Village School | CA27 0AA | North | Football | Unsecured | Grass | Education | St. Bees Village School has one standard quality non-floodlit youth 7v7 pitch offering standard quality ancillary facilities in the form of school changing rooms | 1 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education, FF, FA | M | L
St Benedict’s High School | CA28 8UG | North | Tennis | Unsecured | AGP | Education | Four, recently developed AGP courts on site, all of which are good quality, with good infrastructure. The courts are adjacent to a full size, floodlit AGP, but are not floodlit themselves. | Spare capacity | Protect | Sustain court quality for curricular and community use | M | Education | M | L
St Benedict's Catholic High School | CA28 8UG | North | Netball | Unsecured | AGP | Education | There are 3 high quality AGP courts, overlaid onto tennis. Although there are no floodlights, the courts are immediately adjacent to a full size floodlit 3G, which according to consultation provides some lighting. The site can be booked by clubs and for casual use on the school’s website. The site is easily accessible with good parking. The school and its facilities have recently been redeveloped to a high standard. | No capacity due to lack of floodlighting | Protect, Enhance | Explore the potential for developing floodlighting on netball and tennis courts, to enable winter evening usage. Utilise courts for formal netball demand where possible | M | Education, England Netball | L | H
St Benedicts High School | CA28 8UG | North | Rugby Union | Secured | Grass | Education | Two standard quality non-floodlit senior pitches with access to school changing facilities and a standard maintenance programme | 0 | Protect, Enhance | Improve pitch quality and develop community use agreement | M | Education, RFU | S | L
St Benedicts High School | CA28 8UG | North | Cricket | Unsecured | Grass | School/College/University | One average quality pitch with 4 grass wickets and no artificial turf available for community use | 10 MPS spare | Protect | Sustain pitch quality for curricular use seek community use agreement | M | Education, ECB CCB | M | L
St Benedicts High School | CA28 8UG | North | Football | Unsecured | Grass | Education | Two standard quality 11v11 pitches, one adult and the other youth available with access to the school changing rooms as ancillary facilities | 2 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education, FF, FA | M | L
St Benedicts High School | CA28 8UG | North | AGP | Secured | 3G | Education | One high quality full-sized floodlit 3G pitch which is both FA registered and world rugby compliant with access to the school changing rooms and is home to many clubs | No spare capacity | Protect | Sustain pitch quality and ensure community use is maximised | H | Education, FA, RFU, RFL | L | L
St Benedicts RUFC | CA28 9SH | North | Rugby Union | Secured | Grass | Sports Club | One well maintained good quality non-floodlit local authority owned senior pitch with adequate ancillary facilities in reasonable condition | -2 | Protect, Enhance, Provide | Continue to develop a high quality maintenance regime, in line with GMA recommendations, to ensure grass pitch standards are sustained. Installation of floodlighting to allow for additional mid-week capacity. Explore the possibility of meeting mini and junior demand away from the adult grass pitch at Stage E, which would reduce the current overplay. | L | Sports Club, RFU, CBC | M | H
St Benedicts RUFC | CA28 8UG | North | AGP | Secured | 3G | Sports Club | One standard quality 7v7 floodlit 3G pitch that is world rugby compliant and has good quality ancillary facilities | Spare capacity | Protect | Sustain pitch quality and ensure community use is maximised | L | Club, RFU | L | L
St Benedicts RUFC / Mirehouse FC | CA28 9SW | North | Football | Secured | Grass | Sports Club | One adult 11v11 pitch and ancillary facilities can be found on-site both of which are of high quality | No spare capacity | Protect | Sustain pitch quality for club use | L | RFU, FA, FF, Sports Club | M | L
The Sports Field | CA23 3AE | North | Rugby League | Unsecured | Grass | Sports Club | One good quality senior pitch poorly floodlit, adjacent to the football pitch with no ancillary facilities on site and poor accessibility | 2 MES spare | Protect, Enhance, Provide | Improve pitch quality for community use e.g. drainage | H | CBC | S | M
The Sports Field | CA23 3AE | North | Football | Secured | Grass | Sports Club | One poor quality youth 9v9 pitch with no provisions for any ancillary facilities | 1 MES spare | Protect, Enhance | Improve pitch quality to support additional community use | H | Sports Club | M | L
The Whitehaven Academy | CA28 8TY | North | Rugby Union | Unsecured | Grass | Education | One standard quality senior pitch with no floodlights and access to the school changing rooms as ancillary facilities | 0 | Protect, Enhance | Improve pitch quality through improved maintenance regime and install formal drainage solution. The pitch may be in a key location, due to the development of additional facilities at the school, so a secure community use agreement is necessary. | M | Education, RFU | M | M
The Whitehaven Academy | CA28 8TY | North | Tennis | Secured | Tarmac | Education | The three tarmac courts, overlayed with netball courts on site are all rated as poor, with unsatisfactory fencing and netting. | Spare capacity | Enhance | Provide new tennis court facilities as part of wider development proposals. Project existing courts | H | Education, LTA | S | H
The Whitehaven Academy | CA28 8TY | North | Football | Unsecured | Grass | Education | Two standard quality non-floodlit adult 11v11 pitches with access to the school changing rooms as ancillary facilities | 2 MES spare | Protect, Enhance, Provide | Develop 3G AGP and sand dressed AGP, in accordance with planning application 4/22/2118/0F1. Secure community use agreement for the whole site. Review maintenance regime of grass pithces and improve pitch quality for community use | M | Education, FF, FA | S | H
Thornhill Playing Fields | CA22 2SU | North | Football | Secured | Grass | Sports Club | Thornhill FC's home ground consists of one adult 11v11 and one youth 11v11 both poor quality pitches along with poor ancillary facilities | 1 MES spare | Protect, Enhance | Improve pitch quality to support additional community use | H | CBC, FA, FF, Sports club | M | L
Thornhill Primary School | CA22 2SJ | North | Netball | Unsecured | Tarmac | Education | This is a primary school site, with netball markings overlayed with small sided football. The line markings appear to be recently done, but the court is primarily used for lunch and breaktime provision for the school. | No capacity due to lack of floodlighting | Protect | Sustain court quality for curricular use | L | Education | M | L
Thwaites Village Hall | LA18 5HJ | South | Football | Secured | Grass | Community Organisation | One standard quality non-floodlit adult 11v11 pitch and standard ancillary facilities | 1 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Community organisation | M | L
Thwaites Village Hall | LA18 5HJ | South | Tennis | Secured | Macadam | Community Organisation | One, good quality macadam court, that are owned and operated by the Thwaites Village Hall. The court is open to the community and are not locked and does require pre-booking | Spare capacity | Protect | Sustain court quality for community use | L | CBC, Community Organisation | M | L
Wath Brow Hornets RLFC | CA23 3EW | North | Rugby League | Secured | Grass | Sports Club | One excellent quality pitch on site which has covered perimeter fencing, appropriate markings and easy accessibility with a gym on-site. The club has received Sport England funding in the past | No spare capacity | Protect | Sustain pitch quality through current maintenance regime | L | Sports Club | M | L
West Lakes Academy | CA22 2DQ | North | Rugby Union | Unsecured | Grass | Education | One non-floodlit education site with poor quality pitch with standard maintenance scores and school changing ancillary facilities | 0 | Protect | Improve pitch quality and develop community use agreement | M | Education, RFU | S | L
West Lakes Academy Playing Fields | CA22 2EB | North | Football | Unsecured | Grass | Education | The school site has two standard rated youth 11v11 pitches with access to the school changing rooms as ancillary facilities | 2 MES spare | Protect | Review maintenance regime and sustain pitch quality for community use | M | Education, FF, FA | M | L
Whitehaven Academy | CA28 8TY | North | Rugby League | Unsecured | Grass | Education | One standard quality senior pitch with no floodlights and access to the school changing rooms as ancillary facilities | 2 MES spare | Protect, Enhance, Provide | Explore the potential and need for 3G development that is rugby league compliant as part of Stage E. Improve pitch quality for community use e.g. drainage and maximise community use. Explore the installation of floodlighting to make the grass pitch suitable and available to meet training demand. | M | Education, RFL | S | H
Whitehaven AFC | CA28 9DB | North | Football | Secured | Grass | Sports Club | Two high quality floodlit pitches, one adult 11v11 and the other youth 7v7 pitch with suitable ancillary facilities | No spare capacity | Protect | Explore the potential for 3G development on exisiting grass pitch, as per club aspirations, at Stage E. Relocate all training demand away from grass provision, onto 3G facilities. | H | Sports Club | L | H
Whitehaven AFC | CA28 9DB | North | AGP | Secured | 3G | Sports Club | One good quality full-sized floodlit 3G pitch which is FA registered but not world rugby compliant with quality ancillary facilities | No spare capacity | Protect | Sustain pitch quality and ensure community use is maximised. | H | CBC, FA, FF | L | L
Whitehaven Bowling Club | CA28 9DD | North | Outdoor Bowls | Secured | Grass | Sports Club | 2x 6 rink courts. Good quality. Good but slightly patchy grass. Very busy and active at time of visit. Easy access | Spare capacity | Protect | Ensure site quality does not worsen | L | Sports Club | L | L
Whitehaven Cricket Ground | CA28 7QR | North | Cricket | Secured | Grass | Sports Club | One standard quality pitch with 16 squares and high quality artificial nets. The outfield grass seems to be long and two rugby pitches overlap the cricket ground | No spare capacity | Protect | Sustain pitch quality for club use | H | Club, ECB, CCB | M | L
Whitehaven Miners Social Welfare | CA28 9DD | North | Football | Secured | Grass | Sports Club | One adult 11v11 and one youth 11v11 both poor quality pitches with standard ancillary facilities | No spare capacity | Protect, Enhance | Improve pitch quality to support additional community use, based on recommendations in the completed PP report. Remove training demand from grass pitches and prioritise use of 3G provision | H | Sports Club | S | M
Whitehaven RLFC | CA28 9DD | North | Rugby League | Secured | Grass | Sports Club | Excellent site featuring a top quality floodlit pitch, adjacent to football and bowls clubs. The pitch has covered seating on one side, covered standing on the other, and two sides with uncovered tiered standing. The site is secured with a turnstile entry | 1.5 MES spare | Protect | Sustain pitch quality through current maintenance regime | L | Sports Club | L | L
Whitehaven Rugby Club | CA28 9DD | North | Rugby Union | Secured | Grass | Sports Club | Two non-floodlit senior pitches of standard quality with access to high-quality ancillary facilities and average maintenance scores | 2.25 | Protect | Improve pitch quality through improved maintenance regime that is identified through a GMA pitch assessment | L | Sports Club, RFU | S | L